## sprint3
id | Task | Est. Time | Finished | Who | Time
16 | keep win count | 30 | 2 | R
17 | reset win count | 15 | 2 | R |  | day | progress | remaining
18 | AI | 480 | 7 | CMR |  | 0 |  | 1335
24 | board evaluation function | 120 |  | CMR |  | 7 |  | 0
31 | choose which piece to capture | 90 | 2 | R
32 | determine if multiple pieces can be captured | 90 | 3 | R | 60 | 0 | 0 | 1335
33 | check if another piece can be captured | 45 | 3 | R | 60 | 2 | 135 | 1200
40 | change background to scale | 60 | 3 | M |  | 3 | 270 | 930
46 | prompt for client/server | 45 | 3 | C |  | 5 | 150 | 780
47 | write client | 60 | 7 | M |  | 7 | 660 | 120
48 | write server | 120 | 7 | MC
49 | prompt for board size | 30 | 3 | C
50 | paika | 60 | 5 | C
51 | change board size | 60 | 5 | C
52 | tie condition | 30 | 5 | M
1335