## sprint3
id | Task | Est. Time | Finished | Who | Time
16 | keep win count | 30 | R
17 | reset win count | 15 | R |  |  | day | remaining
18 | AI | 480 | CMR |  |  | 0 | 1335
24 | board evaluation function | 120 | CMR |  |  | 7 | 0
31 | choose which piece to capture | 90 | M
32 | determine if multiple pieces can be captured | 90 | R
33 | check if another piece can be captured | 45 | R
40 | change background to scale | 60 | M
46 | prompt for client/server | 45 | C
47 | write client | 60 | M
48 | write server | 120 | MC
49 | prompt for board size | 30 | C
50 | paika | 60 | C
51 | change board size | 60 | C
52 | tie condition | 30 | M
1335