## sprint2_backlog
id | Task | Est. Time | Finished | Who | Time | Day | Progress | Completed | Remaining
13 | move a piece - click and drag | 120 | 2 | M | 120 | 0 | 0 | 0 | 725 | projection | 0 | 725
15 | new game/reset | 30 | 7 | M | 20 | 2 | 120 | 120 | 605 |  | 7 | 0
11 | remove piece from board | 30 |  |  |  | 7 | 410 | 530 | 195
6 | check if 50 moves played | 30
7 | check if game is over | 30
8 | check if move is valid | 60 | 7 | R | 180
9 | check if a piece can be taken | 75
21 | computer makes a random move | 30
19 | invalid move message | 20 | 7 | M | 20
26 | play again prompt | 30 | 7 | M | 20
37 | turn indicator | 60 | 7 | M | 60
38 | timer display | 45 | 7 | M | 45
39 | time up message | 45 | 7 | M | 45
12 | implement turn time limit | 120 | 7 | M | 120
| total | 725
410