## sprint3
id | Task | Est. Time | Finished | Who | Time
16 | keep win count | 30 |  | R
17 | reset win count | 15 |  | R |  | day | remaining
18 | AI | 480 |  | CMR |  | 0 | 1335
24 | board evaluation function | 120 |  | CMR |  | 7 | 0
31 | choose which piece to capture | 90 |  | R
32 | determine if multiple pieces can be captured | 90 |  | R | 60
33 | check if another piece can be captured | 45 |  | R | 60
40 | change background to scale | 60 |  | M
46 | prompt for client/server | 45 |  | C
47 | write client | 60 |  | M
48 | write server | 120 |  | MC
49 | prompt for board size | 30 |  | C
50 | paika | 60 |  | C
51 | change board size | 60 |  | C
52 | tie condition | 30 |  | M
1335